## Sheet1
Description	Priority	Finished
Ability to initialize Impls with native classes	1.0
Major XML change to support new parser data
Add Structs to XML		04/10/06
Generalized attributes in XML		04/11/06
Generalized attributes in symbol table		04/11/06
Rarray extent expressions in XML		04/04/06
From clause expressions in XML		04/04/06
From clause support in gov.llnl.babel.symbols		04/04/06
From support in backends		04/04/06
Default splicer block being a throw rather than empty		05/08/06
Initial constructors and destructors in C/Fortran could have boilerplate implementation commented out		04/04/06
Ucxx renamed to Cxx		04/06/06
Dcxx ditched		04/06/06
Ucxx namespace goes away		04/06/06
Finish connecting new parser to gov.llnl.babel.symbols		04/04/06
Assertion expressions	Deferred	04/04/06
Add separate bitwise operators &, |, ^, ... in new parser	Deferred	04/04/06
Allow XML overwrites		04/04/06
Pre/post hooks in C++, Fortrans, Java, Python
Translator for XML?
Change # in from clause to .		04/06/06
Add from support to SIDL text backend		04/06/06
Add Structs to Symbol Table (for Tech-X)		04/07/06
Do NOT generate "wrap" methods for classes in the sidl package		05/12/06
Add local keyword

DOCUMENTATION
Backdoor Initializer documented		05/12/06
Local keyword		05/12/06
Generalized attributes
rarray extent expressions
Leading dot		05/16/06
From clause		05/16/06